## Sheet1
Incident ID | Category | Sub Category | Priority | Impact | Urgency | Can Be Assigned To | Related KEDB Article | Description | Open Date | Closed Date | Resolution notes | Resolved by | Created By
INC12345 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3456 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 17-09-2024 19:27 | 01-10-2024 17:27 | Other |  | Chris Johnson
INC12346 | Hardware | Server | 3 | Major | Medium | IT Hardware Support | KEDB-3457 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 11-10-2024 04:27 | 10-10-2024 18:27 | Software | js83793 | Emily Davis
INC12347 | Network | Application | 4 | Minor | Low | Network Operations Team | KEDB-3458 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 08-10-2024 00:27 | 28-09-2024 03:27 | No error - works as designed |  | Robert Brown
INC12348 | Compliance | Client Setup | 3 | Major | High | Compliance Team | KEDB-3459 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 12-09-2024 04:27 |  | Operator error | jh38930 | Chris Johnson
INC12349 | Security | Server | 1 | Critical | High | Security Operations Team | KEDB-3460 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 06-10-2024 01:27 |  | Other |  | John Doe
INC12350 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3461 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 01-10-2024 20:27 |  | Other |  | Robert Brown
INC12351 | Hardware | Server | 3 | Major | Medium | IT Hardware Support | KEDB-3462 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 17-09-2024 09:27 |  | Unknown | ak8393 | Emily Davis
INC12352 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3463 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 09-10-2024 11:27 |  | Other |  | Jane Smith
INC12353 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3464 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 16-09-2024 11:27 | 12-09-2024 03:27 | Other | js83793 | Emily Davis
INC12354 | Security | Cloud | 1 | Critical | High | Security Operations Team | KEDB-3465 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 07-10-2024 23:27 |  | No error - works as designed |  | Robert Brown
INC12355 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3466 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 14-09-2024 19:27 | 21-09-2024 04:27 | Software |  | Jane Smith
INC12356 | Hardware | Infrastructure | 3 | Major | Medium | IT Hardware Support | KEDB-3467 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 16-09-2024 15:27 | 16-09-2024 20:27 | Software | js83793 | John Doe
INC12357 | Network | Client Setup | 4 | Minor | Low | Network Operations Team | KEDB-3468 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 14-09-2024 20:27 | 05-10-2024 11:27 | Software |  | John Doe
INC12358 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3469 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 08-10-2024 09:27 | 09-10-2024 23:27 | Software | js83793 | Jane Smith
INC12359 | Security | Application | 1 | Critical | High | Security Operations Team | KEDB-3470 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 19-09-2024 20:27 | 24-09-2024 09:27 | Data |  | Jane Smith
INC12360 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3471 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 04-10-2024 21:27 |  | Other |  | Emily Davis
INC12361 | Hardware | Cloud | 3 | Major | Medium | IT Hardware Support | KEDB-3472 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 30-09-2024 10:27 |  | Other | bk7480 | Emily Davis
INC12362 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3473 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 18-09-2024 21:27 |  | Unknown |  | John Doe
INC12363 | Compliance | Server | 3 | Major | High | Compliance Team | KEDB-3474 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 14-09-2024 22:27 | 05-10-2024 03:27 | Other | js83793 | John Doe
INC12364 | Security | Infrastructure | 1 | Critical | High | Security Operations Team | KEDB-3475 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 08-10-2024 05:27 | 15-09-2024 06:27 | Other |  | Chris Johnson
INC12365 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3476 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 01-10-2024 19:27 |  | Referred |  | Chris Johnson
INC12366 | Hardware | Cloud | 3 | Major | Medium | IT Hardware Support | KEDB-3477 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 25-09-2024 21:27 | 12-09-2024 13:27 | Software | js83793 | Robert Brown
INC12367 | Network | Server | 4 | Minor | Low | Network Operations Team | KEDB-3478 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 27-09-2024 01:27 | 23-09-2024 03:27 | Other |  | John Doe
INC12368 | Compliance | Server | 3 | Major | High | Compliance Team | KEDB-3479 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 22-09-2024 11:27 |  | No error - works as designed | jh38930 | Emily Davis
INC12369 | Security | Cloud | 1 | Critical | High | Security Operations Team | KEDB-3480 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 08-10-2024 02:27 |  | Software |  | Emily Davis
INC12370 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3481 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 29-09-2024 22:27 |  | Other |  | Chris Johnson
INC12371 | Hardware | Infrastructure | 3 | Major | Medium | IT Hardware Support | KEDB-3482 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 03-10-2024 04:27 | 05-10-2024 23:27 | Other | js83793 | Jane Smith
INC12372 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3483 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 11-09-2024 12:27 |  | No error - works as designed |  | Chris Johnson
INC12373 | Compliance | Server | 3 | Major | High | Compliance Team | KEDB-3484 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 08-10-2024 15:27 |  | Other | js83793 | Emily Davis
INC12374 | Security | Server | 1 | Critical | High | Security Operations Team | KEDB-3485 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 16-09-2024 19:27 | 17-09-2024 19:27 | Other |  | John Doe
INC12375 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3486 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 06-10-2024 03:27 | 18-09-2024 07:27 | Other |  | Jane Smith
INC12376 | Hardware | Infrastructure | 3 | Major | Medium | IT Hardware Support | KEDB-3487 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 23-09-2024 02:27 |  | Other | cd3683 | Robert Brown
INC12377 | Network | Application | 4 | Minor | Low | Network Operations Team | KEDB-3488 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 11-09-2024 15:27 | 02-10-2024 00:27 | Other |  | Jane Smith
INC12378 | Compliance | Server | 3 | Major | High | Compliance Team | KEDB-3489 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 07-10-2024 12:27 |  | Other | js83793 | Jane Smith
INC12379 | Security | Application | 1 | Critical | High | Security Operations Team | KEDB-3490 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 03-10-2024 17:27 | 23-09-2024 18:27 | Other |  | John Doe
INC12380 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3491 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 08-10-2024 22:27 |  | No error - works as designed |  | Emily Davis
INC12381 | Hardware | Infrastructure | 3 | Major | Medium | IT Hardware Support | KEDB-3492 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 01-10-2024 16:27 |  | Software | js83793 | Jane Smith
INC12382 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3493 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 15-09-2024 06:27 | 24-09-2024 15:27 | No error - works as designed |  | Emily Davis
INC12383 | Compliance | Server | 3 | Major | High | Compliance Team | KEDB-3494 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 26-09-2024 17:27 |  | Software | js83793 | John Doe
INC12384 | Security | Cloud | 1 | Critical | High | Security Operations Team | KEDB-3495 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 16-09-2024 03:27 | 26-09-2024 10:27 | Other |  | Jane Smith
INC12385 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3496 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 14-09-2024 15:27 | 30-09-2024 23:27 | No error - works as designed |  | John Doe
INC12386 | Hardware | Infrastructure | 3 | Major | Medium | IT Hardware Support | KEDB-3497 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 09-10-2024 09:27 |  | Other | jh38930 | John Doe
INC12387 | Network | Server | 4 | Minor | Low | Network Operations Team | KEDB-3498 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 06-10-2024 03:27 |  | Other |  | Jane Smith
INC12388 | Compliance | Server | 3 | Major | High | Compliance Team | KEDB-3499 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 01-10-2024 10:27 | 14-09-2024 01:27 | Other | rt58956 | Robert Brown
INC12389 | Security | Server | 1 | Critical | High | Security Operations Team | KEDB-3500 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 13-09-2024 15:27 |  | Data |  | Jane Smith
INC12390 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3501 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 03-10-2024 03:27 |  | Software |  | Chris Johnson
INC12391 | Hardware | Infrastructure | 3 | Major | Medium | IT Hardware Support | KEDB-3502 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 12-09-2024 15:27 |  | Other | rt58956 | John Doe
INC12392 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3503 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 06-10-2024 21:27 |  | Other |  | John Doe
INC12393 | Compliance | Server | 3 | Major | High | Compliance Team | KEDB-3504 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 01-10-2024 11:27 |  | Other | rt58956 | Robert Brown
INC12394 | Security | Cloud | 1 | Critical | High | Security Operations Team | KEDB-3505 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 15-09-2024 13:27 |  | Software |  | Emily Davis
INC12395 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3506 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 28-09-2024 04:27 | 07-10-2024 19:27 | No error - works as designed |  | Emily Davis
INC12396 | Hardware | Cloud | 3 | Major | Medium | IT Hardware Support | KEDB-3507 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 26-09-2024 10:27 | 01-10-2024 21:27 | No error - works as designed | rt58956 | Chris Johnson
INC12397 | Network | Application | 4 | Minor | Low | Network Operations Team | KEDB-3508 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 28-09-2024 21:27 |  | Other |  | Jane Smith
INC12398 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3509 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 13-09-2024 01:27 | 15-09-2024 07:27 | Software | rt58956 | Robert Brown
INC12399 | Security | Application | 1 | Critical | High | Security Operations Team | KEDB-3510 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 30-09-2024 05:27 |  | Unknown |  | Jane Smith
INC12400 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3511 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 16-09-2024 10:27 | 22-09-2024 00:27 | Other |  | Emily Davis
INC12401 | Hardware | Cloud | 3 | Major | Medium | IT Hardware Support | KEDB-3512 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 17-09-2024 06:27 |  | Other | rt58956 | Emily Davis
INC12402 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3513 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 16-09-2024 19:27 | 21-09-2024 23:27 | Software |  | Emily Davis
INC12403 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3514 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 06-10-2024 10:27 | 27-09-2024 18:27 | Software | rt58956 | Chris Johnson
INC12404 | Security | Cloud | 1 | Critical | High | Security Operations Team | KEDB-3515 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 25-09-2024 10:27 | 25-09-2024 00:27 | Other |  | John Doe
INC12405 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3516 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 13-09-2024 09:27 |  | Other |  | Jane Smith
INC12406 | Hardware | Server | 3 | Major | Medium | IT Hardware Support | KEDB-3517 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 12-09-2024 11:27 |  | Other | rt58956 | Chris Johnson
INC12407 | Network | Client Setup | 4 | Minor | Low | Network Operations Team | KEDB-3518 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 02-10-2024 17:27 |  | Hardware |  | Chris Johnson
INC12408 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3519 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 22-09-2024 04:27 |  | Other | rt58956 | Emily Davis
INC12409 | Security | Infrastructure | 1 | Critical | High | Security Operations Team | KEDB-3520 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 23-09-2024 09:27 |  | Other |  | Chris Johnson
INC12410 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3521 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 11-10-2024 06:27 | 14-09-2024 00:27 | Software |  | Robert Brown
INC12411 | Hardware | Server | 3 | Major | Medium | IT Hardware Support | KEDB-3522 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 17-09-2024 20:27 |  | Other | js83793 | Chris Johnson
INC12412 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3523 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 26-09-2024 20:27 | 05-10-2024 20:27 | Unknown |  | Jane Smith
INC12413 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3524 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 02-10-2024 09:27 |  | Other | js83793 | Emily Davis
INC12414 | Security | Application | 1 | Critical | High | Security Operations Team | KEDB-3525 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 19-09-2024 05:27 | 01-10-2024 20:27 | No error - works as designed |  | John Doe
INC12415 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3526 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 17-09-2024 00:27 |  | Other |  | John Doe
INC12416 | Hardware | Server | 3 | Major | Medium | IT Hardware Support | KEDB-3527 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 01-10-2024 19:27 |  | Other | js83793 | Robert Brown
INC12417 | Network | Application | 4 | Minor | Low | Network Operations Team | KEDB-3528 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 21-09-2024 10:27 | 17-09-2024 06:27 | Other |  | John Doe
INC12418 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3529 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 04-10-2024 03:27 |  | Other | js83793 | Jane Smith
INC12419 | Security | Cloud | 1 | Critical | High | Security Operations Team | KEDB-3530 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 18-09-2024 12:27 | 12-09-2024 00:27 | Other |  | Emily Davis
INC12420 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3531 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 11-09-2024 16:27 |  | Software |  | Emily Davis
INC12421 | Hardware | Server | 3 | Major | Medium | IT Hardware Support | KEDB-3532 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 19-09-2024 16:27 | 23-09-2024 03:27 | Unknown | js83793 | John Doe
INC12422 | Network | Server | 4 | Minor | Low | Network Operations Team | KEDB-3533 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 21-09-2024 08:27 |  | Other |  | Robert Brown
INC12423 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3534 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 17-09-2024 03:27 |  | Other | js83793 | Chris Johnson
INC12424 | Security | Server | 1 | Critical | High | Security Operations Team | KEDB-3535 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 26-09-2024 16:27 | 21-09-2024 19:27 | Other |  | Jane Smith
INC12425 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3536 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 26-09-2024 17:27 | 04-10-2024 09:27 | Unknown |  | John Doe
INC12426 | Hardware | Server | 3 | Major | Medium | IT Hardware Support | KEDB-3537 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 15-09-2024 17:27 | 13-09-2024 09:27 | Other | js83793 | Emily Davis
INC12427 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3538 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 15-09-2024 16:27 |  | Other |  | John Doe
INC12428 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3539 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 03-10-2024 19:27 |  | Other | jh38930 | Jane Smith
INC12429 | Security | Application | 1 | Critical | High | Security Operations Team | KEDB-3540 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 09-10-2024 20:27 | 29-09-2024 20:27 | Other |  | Emily Davis
INC12430 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3541 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 03-10-2024 21:27 |  | Software |  | Chris Johnson
INC12431 | Hardware | Infrastructure | 3 | Major | Medium | IT Hardware Support | KEDB-3542 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 18-09-2024 09:27 | 04-10-2024 07:27 | Other | jh38930 | Emily Davis
INC12432 | Network | Application | 4 | Minor | Low | Network Operations Team | KEDB-3543 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 12-09-2024 01:27 |  | No error - works as designed |  | Chris Johnson
INC12433 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3544 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 30-09-2024 20:27 |  | Software | jh38930 | Robert Brown
INC12434 | Security | Cloud | 1 | Critical | High | Security Operations Team | KEDB-3545 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 10-10-2024 01:27 |  | Other |  | John Doe
INC12435 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3546 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 17-09-2024 17:27 | 12-09-2024 01:27 | Other |  | Chris Johnson
INC12436 | Hardware | Cloud | 3 | Major | Medium | IT Hardware Support | KEDB-3547 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 20-09-2024 04:27 | 01-10-2024 09:27 | Other | jh38930 | John Doe
INC12437 | Network | Cloud | 4 | Minor | Low | Network Operations Team | KEDB-3548 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 06-10-2024 19:27 | 07-10-2024 16:27 | Other |  | Robert Brown
INC12438 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3549 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 14-09-2024 06:27 |  | Other | jh38930 | Chris Johnson
INC12439 | Security | Infrastructure | 1 | Critical | High | Security Operations Team | KEDB-3550 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 18-09-2024 13:27 |  | Unknown |  | Chris Johnson
INC12440 | Software | Application | 1 | Critical | High | Application Support Team | KEDB-3551 | Onboarding application crashes when users try to submit their KYC documents, affecting all new customer onboarding processes. | 21-09-2024 17:27 | 27-09-2024 11:27 | Software |  | Chris Johnson
INC12441 | Hardware | Server | 3 | Major | Medium | IT Hardware Support | KEDB-3552 | Server hosting the onboarding application is experiencing performance degradation, slowing down onboarding for some users. | 07-10-2024 15:27 |  | Questions | jh38930 | Robert Brown
INC12442 | Network | Client Setup | 4 | Minor | Low | Network Operations Team | KEDB-3553 | Connectivity issues between the application and database servers, causing intermittent failures in the onboarding process. | 21-09-2024 05:27 | 12-09-2024 16:27 | Operator error |  | Emily Davis
INC12443 | Compliance | Application | 3 | Major | High | Compliance Team | KEDB-3554 | Customer details in onboarding system not syncing with compliance systems, leading to failed background checks. | 05-10-2024 19:27 | 04-10-2024 23:27 | Unknown | jh38930 | Chris Johnson
INC12444 | Security | Server | 1 | Critical | High | Security Operations Team | KEDB-3555 | Potential security breach detected in the onboarding application where user data may have been compromised. Immediate action required. | 29-09-2024 23:27 |  | Other |  | John Doe